Lead Selection Governance Record

Demo programme | 12 July 2026 | Synthetic demonstration data

This record is illustrative only. It is designed to demonstrate structured rationale, evidence snapshots, dissent, conditions and reconsideration triggers.

Decision

| Question | Which construct should advance into candidate-nomination studies? |
| --- | --- |
| Outcome | Advance A17-03; retain A17-05 as backup. |
| Approver | Discovery Governance Committee |
| Status | Approved |
| Effective date | 12 July 2026 |

Rationale

A17-03 combined the strongest potency, receptor internalisation and early developability profile. Governance accepted expression heterogeneity as a biomarker-development risk rather than a reason to stop. The decision did not conclude that normal-tissue risk or formulation readiness were resolved.

Evidence snapshot at the time of decision

| Evidence object | Finding available at the time | Decision use | State |
| --- | --- | --- | --- |
| E-003 | Rapid receptor internalisation in high-expression models. | Supports construct mechanism. | Accepted |
| E-006 | Sub-nanomolar potency in high-expression models. | Supports lead selection. | Accepted |
| E-007 | Limited activity in low-expression models. | Creates biomarker dependency. | Accepted |
| E-015 | Early freeze-thaw profile within target. | Supports developability. | Accepted |

Dissent and accepted risks

Safety representative dissent: expand normal-tissue binding and cross-reactivity work earlier than the proposed plan.

Biomarker cut-off not locked.

Normal-tissue panel incomplete.

Subcutaneous formulation not yet demonstrated.

Conditions and owners

| Condition | Owner | Due | Completion evidence |
| --- | --- | --- | --- |
| Expand normal-tissue panel | Safety Sciences | 2 Oct 2026 | Versioned tissue-binding assessment |
| Confirm activity in patient-derived models | In Vivo Pharmacology | 27 Sep 2026 | PDX evidence set |
| Start high-concentration formulation screen | Biologics CMC | 14 Nov 2026 | Formulation recommendation |

Reconsideration triggers

Clinically relevant class toxicity emerges.

Biomarker strategy cannot define a responsive patient segment.

Developability requires material construct change.

Audit

Decision record owner: Programme Governance. Any subsequent update must create a new version and preserve the evidence snapshot used for this decision.